## Pre-Audit Action Plan (2)
Pre-Audit Corrective Action Plan & Findings Register
Action plan for pre-audit remarks, responsible persons, locations, status, and progress tracking.
№ | Audit Finding / Remark | Photos | Risk Level | Location / Area | Responsible Person | Target Date | Status | Close out Photos | Comments / Progress Report
1 | Request an official written refusal/clarification regarding diesel fuel storage license from relevant authorities. | N/A | High | Legal / Regulatory | HSE Dept/Utility | 2026-10-07 | Closed | #VALUE! | Drafting formal request letter.
2 | Inspect and verify regulatory licenses/certificates for all mandatory plant equipment. | N/A | High | Plant-wide | TEAM | 2026-10-20 | In Progress | #VALUE! | Reviewing equipment passports and compliance documents.
3 | Perform quality compliance check and collect QA certificates for all critical production materials. | N/A | Medium | Warehouse / QA | Gulnoza/Orif/ | 2026-11-15 | In Progress | #VALUE!
4 | Implement LOTO (Lockout/Tagout) system improvements and update isolation points. | #VALUE! | High | Production Lines | HSE Dept | 2026-10-28 | In Progress | #VALUE! | Create LOTO map.(GAP assestment).Check LOTO training.
5 | Install noise dampening enclosures/insulation to reduce equipment acoustic impact. | #VALUE! | Medium | Hot Line / Air Conveyor | Xudoyberdi | 2026-10-15 | Open |  | Not applicable for our plant
6 | Audit LOTO padlocks and ensure unique keys are properly assigned and managed. | #VALUE! | High | Production | Feruz | 2026-09-28 | Closed | #VALUE!
7 | Compile MSDS documents and establish chemical compatibility matrix. | #VALUE! | High | Chemical Storage / Labs | Gulnoza | 2026-10-10 | Closed | #VALUE!
8 | Procure professional flashlights for engineering and maintenance staff. | #VALUE! | Low | Production | Bakhodir | 2026-12-15 | In Progress |  | We are workin on it
9 | Install physical safety fencing at the end of RGB packaging robot line or optimize motion sensors/light curtains to prevent human entry. | #VALUE! | High | Packaging Line (RGB) | Munis | 2026-10-31 | In Progress |  | It will be done inter-nal resources
10 | Install warning signage and implement confined space entry registration log at the bottle washer. | #VALUE! | High | Bottle Washing Area | HSE Feruz | 2026-09-28 | Closed | #VALUE! | Partialy completed Warning signages will be installed soon
11 | The air conveyor system was observed operating with an open or missing protective screen in the working zone of the bottle transport path. | #VALUE! | High | Hot Line / Air Conveyor | Production | 2026-09-28 | Closed | #VALUE!
12 | Install safety signage across the warehouse and plant stating that mobile equipment/forklifts must yield right-of-way to pedestrians. | #VALUE! | High | Warehouse & Production | Feruz/Bakhodir | 2026-11-30 | In Progress |  | Designing pedestrian/traffic safety signs.
13 | Ensure all contract cleaning personnel (CCI washing contractors) wear high-visibility reflective workwear. | N/A | High | Plant / Washing Team | Bakhodir | 2026-10-15 | Closed | #VALUE! | #VALUE!
14 | Install Emergency Eye Wash stations near all chemical handling areas inside of production, complete with inspection checklists and usage instructions. | #VALUE! | High | Chemical / Production Areas | Adem Tatar | 2026-11-30 | Open
15 | Clean and remove surface paint residues from the drainage system. | #VALUE! | Medium | Plant Drainage / Production | Facilities / Utility | 2026-09-28 | In Progress | #VALUE! | ucrete epoxy will be done during annual OH of line,meanwhile we will ensure deep cleaning regularlyu to avoid microbial growth
16 | Shorten cable lengths for equipment JOG manual control pendants to ensure safe operation. | N/A | High | Production Lines | Xasanjon Shonazarov | 2026-10-20 | Open |  | We will buy double hand JOG from Krones
17 | Ensure standard operating procedures (SOPs) are available and posted at all palletizers. | #VALUE! | Medium | Palletizing Area | Production Supervisors | 2026-09-28 | Closed | #VALUE!
18 | Inspect all respirators for expiration dates and replace filters or units as necessary. | #VALUE! | High | HSE | Feruz | 2026-11-30 | In Progress |  | Inventory audit of respiratory completed. All expired respirarosr will be replaced.
19 | The fire extinguisher cabinet in the Raw Material zone is blocked by a large volume of stacked materials. | #VALUE! | Critical | Warehouse | Orif | 2026-10-15 | Closed | #VALUE!
20 | Locate existing Emergency Action Plan or develop/update one if missing. | N/A | Critical | Plant | Bakhodit/Feruz | 2026-10-15 | In Progress | #VALUE! | Reviewing existing documentation and updating emergency response procedures.
21 | During conveyor inspection, missing bolts were identified on one of the conveyor units. | #VALUE! | Critical | Production | Feruz/Bakhodir | 2026-10-15 | Closed | #VALUE!

## Pre-Audit Action Plan
Pre-Audit Corrective Action Plan & Findings Register
Action plan for pre-audit remarks, responsible persons, locations, status, and progress tracking.
№ | Audit Finding / Remark | Photos | Risk Level | Location / Area | Responsible Person | Target Date | Status | Close out Photos | Comments / Progress Report
1 | Request an official written refusal/clarification regarding diesel fuel storage license from relevant authorities. |  | High | Legal / Regulatory | HSE Dept/Utility | 2026-10-07 | Closed | #VALUE! | Drafting formal request letter.
2 | Inspect and verify regulatory licenses/certificates for all mandatory plant equipment. |  | High | Plant-wide | TEAM | 2026-10-20 | In Progress | #VALUE! | Reviewing equipment passports and compliance documents.
3 | Perform quality compliance check and collect QA certificates for all critical production materials. |  | Medium | Warehouse / QA | Gulnoza/Orif/ | 2026-11-15 | In Progress | #VALUE!
4 | Implement LOTO (Lockout/Tagout) system improvements and update isolation points. |  | High | Production Lines | HSE Dept | 2026-10-28 | In Progress | #VALUE! | Create LOTO map.(GAP assestment).Check LOTO training.
5 | Install noise dampening enclosures/insulation to reduce equipment acoustic impact. |  | Medium | Hot Line / Air Conveyor | Xudoyberdi | 2026-10-15 | Open |  | Not applicable for our plant
6 | Audit LOTO padlocks and ensure unique keys are properly assigned and managed. |  | High | Production | Feruz | 2026-09-28 | Closed | #VALUE!
7 | Compile MSDS documents and establish chemical compatibility matrix. |  | High | Chemical Storage / Labs | Gulnoza | 2026-10-10 | Closed | #VALUE!
8 | Procure professional flashlights for engineering and maintenance staff. |  | Low | Production | Bakhodir | 2026-12-15 | In Progress |  | We are workin on it
9 | Install physical safety fencing at the end of RGB packaging robot line or optimize motion sensors/light curtains to prevent human entry. |  | High | Packaging Line (RGB) | Munis | 2026-10-31 | In Progress |  | It will be done inter-nal resources
11 | Install warning signage and implement confined space entry registration log at the bottle washer. |  | High | Bottle Washing Area | HSE Feruz | 2026-09-28 | Closed | #VALUE! | Partialy completed Warning signages will be installed soon
12 | The air conveyor system was observed operating with an open or missing protective screen in the working zone of the bottle transport path. | #VALUE! | High | Hot Line / Air Conveyor | Production | 2026-09-28 | Closed | #VALUE!
13 | Install safety signage across the warehouse and plant stating that mobile equipment/forklifts must yield right-of-way to pedestrians. |  | High | Warehouse & Production | Feruz/Bakhodir | 2026-11-30 | In Progress |  | Designing pedestrian/traffic safety signs.
14 | Ensure all contract cleaning personnel (CCI washing contractors) wear high-visibility reflective workwear. |  | High | Plant / Washing Team | Bakhodir | 2026-10-15 | Closed | #VALUE! | #VALUE!
15 | Install Emergency Eye Wash stations near all chemical handling areas inside of production, complete with inspection checklists and usage instructions. |  | High | Chemical / Production Areas | Adem Tatar | 2026-11-30 | Open
16 | Clean and remove surface paint residues from the drainage system. | #VALUE! | Medium | Plant Drainage / Production | Facilities / Utility | 2026-09-28 | In Progress | #VALUE! | ucrete epoxy will be done during annual OH of line,meanwhile we will ensure deep cleaning regularlyu to avoid microbial growth
17 | Shorten cable lengths for equipment JOG manual control pendants to ensure safe operation. |  | High | Production Lines | Xasanjon Shonazarov | 2026-10-20 | Open |  | We will buy double hand JOG from Krones
18 | Ensure standard operating procedures (SOPs) are available and posted at all palletizers. |  | Medium | Palletizing Area | Production Supervisors | 2026-09-28 | Closed | #VALUE!
19 | Inspect all respirators for expiration dates and replace filters or units as necessary. |  | High | HSE | Feruz | 2026-11-30 | Open |  | Inventory audit of respiratory completed. All expired respirarosr will be replaced.
20 | The fire extinguisher cabinet in the Raw Material zone is blocked by a large volume of stacked materials. |  | Critical | Warehouse | Orif | 2026-10-15 | Closed | #VALUE!
21 | Locate existing Emergency Action Plan or develop/update one if missing. |  | Critical | Plant | Bakhodit/Feruz | 2026-10-15 | In Progress | #VALUE! | Reviewing existing documentation and updating emergency response procedures.